## NETWORKDAYS
Using the NETWORKDAYS and NETWORKDAYS.INT Functions
Task Name | Start Date | Work Days | Work Days (INTL) | Finish Date | UK Holidays (2020)
Research | 2020-01-01 | 5 | 5 | 2020-01-08
Book Venue | 2020-01-07 | 1 | 1 | 2020-01-08 | 2020-01-01 | New Year's Day
Order Wedding Dress | 2020-01-09 | 3 | 3 | 2020-01-14 | 2020-04-02 | Good Friday'2 April (Friday): Good Friday
Order Bridesmaids Dress | 2020-01-11 | 3 | 3 | 2020-01-15 | 2020-04-05 | Easter Monday'5 April (Monday): Easter Monday
Book Caterer | 2020-01-13 | 2 | 2 | 2020-01-15 | 2020-05-03 | May Day bank holiday'3 May (Monday): May Day bank holiday
Book Photographer | 2020-01-17 | 2 | 2 | 2020-01-21 | 2020-05-31 | Spring Bank Holiday'31 May (Monday): Spring Bank Holiday
Order Flowers | 2020-01-20 | 1 | 1 | 2020-01-21 | 2020-08-30 | Summer Bank Holiday (not Scotland)'30 August (Monday): Summer Bank Holiday (not Scotland)
Order Cake | 2020-01-23 | 1 | 1 | 2020-01-24 | 2020-12-25 | Christmas Day'25 December (Saturday): Christmas Day
Send Invitations | 2020-01-25 | 4 | 4 | 2020-01-30 | 2020-12-26 | Boxing Day'26 December (Sunday): Boxing Day
Finalize Guest List | 2020-01-27 | 8 | 8 | 2020-02-06 | 2020-12-27 | Christmas Day holiday'27 December (Monday): Christmas Day holiday
Book Honeymoon | 2020-01-28 | 4 | 4 | 2020-02-03 | 2020-12-28 | Boxing Day holiday'28 December (Tuesday): Boxing Day holiday
Task Name | Start Date | End Date | Network Days | Network Days (INTL)
Research | 2020-01-01 | 2020-04-03
Book Venue | 2020-01-07 | 2020-01-14
Order Wedding Dress | 2020-01-09 | 2020-01-13
Order Bridesmaids Dress | 2020-01-11 | 2020-01-15
Book Caterer | 2020-01-13 | 2020-01-28
Formulas:
Finish Date = WORKDAY([Start Date],[Work Days],G5:G14)